| Content of services: Providing MHPSS group counselling services in the framework of the “To improve access to lifesaving services for the most vulnerable children and families affected by the crisis in Khersonska, Dnipropetrovska and Kharkivska Oblasts” project financed by WVI-ADH |  | The result of service provision/performance of works | The term of execution and the place of providing the service |
| --- | --- | --- | --- |
| 1. | Piloting MHPSS group counselling, and recreational activities to shift children away from addiction to functional positive coping mechanism in Khersonska and Kharkivska oblasts: - Adapting the recommendations and guidelines provided in the “SUGGESTIONS FOR UNIVERSAL AND TARGETED PREVENTION INTERVENTIONS FOR YOUNG PEOPLE IN UKRAINE: KHERSON AND KHARKIV” methodological document, preparation of MHPSS group counselling curricula (blueprints) | - MHPSS group counselling curricula (blueprints) and package of training materials | - Term of execution: 1st of June 2024-30th of June 2024 - Place of providing the service: Kharkiv and Kherson Oblasts (offline and/or online) |
|  | - Organizing MHPSS group counselling groups in Kharkiv and Kherson oblasts: - Number of MHPSS group counselling groups: 8 - Number of participants per MHPSS group counselling groups: minimum of 8 and maximum of 12. - Number of participants altogether: minimum of 80 - Participants of MHPSS counselling groups: children and young people between 12-18 years living in Kherson and Kharkiv oblasts - Composition of MHPSS group counselling groups: - Separate groups for teenagers between 12 and 14 years - Separate groups for teenagers between 14 and 18 years | - Consent forms signed by official caregivers of MHPSS group counselling participants - Participant lists of MHPSS group counselling group members. Minimal data content required: - Name - Phone number - Sex - Age - Vulnerability criteria - Relocation status - Place of residence - Place of origin |  |
|  | - Provision of MHPSS group counselling - Expected professional capacities: qualified and experienced child protection professionals (e.g. psychologists, social workers, child protection consultants, education professionals with child protection specialization etc.) - 3 hours of preparation and 12 hours of group counselling/group - Altogether 120 hours | - Attendance sheets (8 groups x 12 hours) - Photo documentation |  |
|  | - Evaluation of piloting drug prevention group counselling based on: - the pre-intervention expectations of participants - the post-intervention opinion of participants on the group counselling services - the observations of the professionals facilitating the MHPSS group counselling sessions | - Pre- and post-intervention questionnaires from each MHPSS group counselling group - Training reports from each MHPSS group counselling group. |  |